## README
Week 0 Control Board
Gate G0 · 21 October 2026 · tracks decisions, external clocks and Sprint 0 delivery
G0 passes when | All 14 ADRs signed · Meta verification submitted · pilot content owner named with dates · fixture hotel seeded · funding path decided.
Two hard blockers | D1 (tenancy) and D5 (citation granularity) must be signed before any Sprint 1 code. Both are expensive to reverse and cheap to decide.
External clock | Meta business verification: assume 4-6 weeks. Web chat is the launch surface precisely because this clock is unreliable.
How to use
02 · ADRs | Item IDs match 07-master-backlog.xlsx exactly (W00-01 to W00-20). If the two disagree, the backlog wins.
03 · Week 0 | Twenty tasks across three tracks. Update Status daily; G0 review Friday.
04 · Verification | The Meta document pack. A name mismatch between RFC, bank statement and website is the classic multi-week rejection.
05 · Pilot recruit | If rows 1-5 of this checklist fail, this is not the pilot property.
06 · Sprint 1 ready | The check that gates Monday morning.

## 02 · ADRs
Architecture decision records — sign-off
Status: Proposed / Accepted / Rejected. Only Accepted is binding.
ID | Decision | Ruling | Reversibility | Status | Approved by / date
D1 | Tenancy enforcement | Postgres RLS on every tenant table AND app-layer guard AND a CI suite asserting 403/404 on foreign IDs. All three, not a choice. | Hard | Proposed
D2 | Retrieval strategy | FTS + trigram + pgvector column populated from day one. Ranking starts simple, tuned after the eval harness exists. | Easy | Proposed
D3 | Embeddings | Generate and store for every published article version even if early ranking ignores them. | Easy | Proposed
D4 | AI output contract | Structured JSON: decision, answer, language, citations, reason_code, topic_keys_used, confidence. No free-text output anywhere. | Hard | Proposed
D5 | Citation granularity | Citations reference article_version_id, never article_id. | Hard | Proposed
D6 | AI operating modes | Auto / Draft / Human-only / After-hours per property. New property defaults to Auto with a tight escalation policy. | Easy | Proposed
D7 | Message sending | Transactional outbox + worker + backoff + DLQ. Never send inside a request handler. | Easy | Proposed
D8 | Webhook handling | Verify signature, dedupe on provider message ID, ack <3s, process async. | Easy | Proposed
D9 | Staff notifications | Email on request/handoff by default, phone-first inbox as primary surface, signed outbound webhook for groups. | Easy | Proposed
D10 | Analytics | Append-only events table + documented taxonomy + nightly SQL rollups. No pipeline, no vendor. | Easy | Proposed
D11 | WhatsApp provider | Direct Cloud API or BSP with Embedded Signup. Hard requirement: hotel owns and retains its number and WABA. | Hard | Proposed
D12 | LLM provider | Primary + fallback behind an internal interface. Models pinned by version, never a floating alias. | Easy | Proposed
D13 | File storage | Managed object storage, signed URLs, virus scan, no public buckets. | Easy | Proposed
D14 | Staff i18n | String catalogue from first commit; Spanish and English at launch. | Expensive later | Proposed

## 03 · Week 0
Sprint 0 task board
Three tracks: A decisions & docs · B external clocks · C engineering
ID | Track | Task | Owner | Day | Depends on | Done when | Status
W00-01 | A | ADR review meeting, D1–D14 | Founder + tech lead | Mon | — | All fourteen discussed; approvers assigned | ☐ Not started
W00-02 | A | Sign D1, D5, D11, D14 (irreversible set) | Founder | Tue | S0-01 | Signed and committed to repo | ☐ Not started
W00-03 | A | Sign remaining ten ADRs | Founder | Wed | S0-02 | Signed | ☐ Not started
W00-04 | A | Funding path decision | Founder | Thu | — | Bootstrap / Funded / Group-led recorded | ☐ Not started
W00-05 | A | Second developer scoped (if funded) | Founder | Thu | S0-04 | Named, start date, scoped to UI + content ops | ☐ Not started
W00-06 | A | One-page non-goals doc | Founder | Wed | — | PMS absent from the roadmap, in writing | ☐ Not started
W00-07 | B | Verification pack assembled and cross-checked | Founder | Tue | — | Six documents, names match | ☐ Not started
W00-08 | B | Submit Meta business verification | Founder | Wed | S0-07 | Case ID recorded | ☐ Not started
W00-09 | B | WhatsApp BSP shortlist to two | Tech lead | Fri | S0-08 | Scored on Embedded Signup + number ownership | ☐ Not started
W00-10 | B | Pilot property kickoff call | Founder | Thu | — | Content owner named with dates | ☐ Not started
W00-11 | C | Repo, branch protection, org setup | Tech lead | Mon | — | main protected; PR template | ☐ Not started
W00-12 | C | CI skeleton: lint, typecheck, test, preview | Tech lead | Tue | S0-11 | A PR produces a preview URL | ☐ Not started
W00-13 | C | Three environments: local, staging, prod | Tech lead | Wed | S0-12 | No shared DB between staging and prod | ☐ Not started
W00-14 | C | Error tracking + structured logging | Tech lead | Thu | S0-13 | Error carries org_id, property_id, conversation_id | ☐ Not started
W00-15 | C | Golden set v1: format + 20 starter questions | Tech lead + founder | Tue | — | Escalation cases written by hand | ☐ Not started
W00-16 | C | Baseline question log started with hotel | Founder | Fri | S0-10 | Front desk logging real questions | ☐ Not started
W00-17 | C | Adversarial fixture hotel built | Tech lead | Fri | S0-13 | Messy content merged; seeds run in staging | ☐ Not started
W00-18 | A | Privacy notice + DPA to Mexican counsel | Founder | Wed | — | Sent; turnaround expected | ☐ Not started
W00-19 | C | Event taxonomy written | Tech lead | Fri | — | 18 events, each with tenant context | ☐ Not started
W00-20 | A | G0 review | Founder + tech lead | Fri | All | Every row ticked; unsigned ADRs block Sprint 1 | ☐ Not started

## 04 · Verification
Meta business verification pack
Submit Wednesday even if imperfect — a rejection is information, waiting is not.
Document | Check before submitting | Matching name? | Attached? | Notes
Legal entity name | Exactly as printed on the RFC. No trading name, no abbreviation.
RFC document | Current, legible, entity matches the name above.
Utility bill (CFE) or bank statement | In the registered business name, address matching the record.
Website | Live, domain matching the business, real contact page.
Display name | The name the hotel actually trades under; not generic.
Phone number | Can receive the verification call in business hours.
Case ID / receipt
A mismatch between RFC, bank statement and website is the single most common cause of a multi-week rejection loop. Check all three against each other before submitting.

## 05 · Pilot recruit
Pilot property recruitment checklist
If rows 1-5 fail, this is not the pilot property.
Item | Requirement | Met? | Evidence / name / date
Rooms | 40+ rooms, or a strong F&B / spa mix that generates questions.
Content owner | Named individual, 4-6 hours in weeks 1-3, dates on the calendar.
GM / front-office owner | Will own the inbox and the weekly review.
Guest directory | Exists and is roughly current.
Channel agreement | Web-first for the pilot; WhatsApp later.
Baseline week | Agrees to one week of manual question logging before launch.
Notification contact | Named on-call person and business hours.
Escalation path | Who handles complaints, medical and billing after hours.

## 06 · Sprint 1 ready
Sprint 1 readiness gate
Check | Pass? | Why it blocks
D1 tenancy signed |  | Without it, schema design starts in the wrong place and RLS is retrofitted
D5 citation granularity signed |  | Decides the article_versions table shape on day one
D2/D3 retrieval decisions signed |  | Chunk and embedding tables are built in Sprint 1
Repo + CI + three environments live |  | Sprint 1 ends with the isolation suite running in CI
Fixture hotel exists in staging |  | Retrieval cannot be developed against content that does not exist
Pilot content owner confirmed with dates |  | Determines whether G1 lands at W3 or slips
Event taxonomy written |  | Events are emitted from Sprint 6; retrofitting is lossy
Funding path decided |  | Determines team shape and therefore the schedule

## 07 · Load
Week 0 load check
Twenty tasks across three tracks, deliberately. No product code this week.
Owner | Tasks | Assessment
Founder | 11 | A full week, and the right use of it: decisions, the two external clocks, and the pilot relationship.
Tech lead | 8 | Deliberately no product code. Infrastructure, CI, fixture hotel, event taxonomy.
Both | 1 | The G0 review on Friday — joint by design.
If one person holds both roles | Sequence: verification Wednesday, funding decision Friday, and accept that the fixture hotel moves to Monday of W1. Something has to give; choose it in advance rather than discovering it Friday evening.