## README
Master Sprint Backlog v2
Single source of truth for the build · 80 items · 14 sprints · 21 Oct 2026
The numbers
Lean pilot path | 69.75 dev-days across 14 sprints (W00, S01–S13). Pilot live Monday of W14.
WhatsApp track | 7.75 dev-days, built W14–16 after the pilot. Tracked separately so it cannot creep in.
Deferred to MVP-1.5 | 1.50 dev-days.
Total backlog | 79.00 dev-days across 80 items.
Capacity | 14 sprints x 5 productive days = 70 days.
Slack | 0.25 days unallocated. W13 carries 2.00 days of launch work, leaving ~3 days of carry-forward room in that week.
What changed in v2
One ID scheme | IDs are now <sprint>-<nn>, so the ID tells you the sprint. v1 had 14 ID collisions with the Week 0 kickoff pack — S0-02 meant two different things in two documents.
S13 was empty | The launch sprint had no items. It now holds staff training, content corrections and the GM go/no-go.
Acceptance criteria | Every item now has a testable acceptance criterion, not a vague definition of done. 'Pool hours answered by lookup, not generation' beats 'facts work'.
Week 0 reconciled | The 20 Week 0 tasks now match the kickoff pack exactly, one-to-one.
How to read it
02 · Sprint ladder | 14 sprints: goal, items, days, cumulative weeks, gate, exit criterion.
03 · Master backlog | All 80 items with sprint, track, estimate, dependency and acceptance criteria. The working board.
04 · Capacity | Demand vs capacity per sprint, split by owner.
05 · Gates | Gates mapped to the sprint that closes them.
06 · Critical path | The dependency chain that sets the launch date.
07 · WhatsApp | 7.75 days, outside the pilot path.
08 · Deferred | What is deliberately out of the pilot.

## 02 · Sprint ladder
Sprint ladder — 14 sprints to pilot
Cumulative weeks is the true elapsed position. Work completes at 13.95 weeks; W14 is launch.
Sprint | Week | Name | Goal | Items | Dev-days | Cum. days | Cum. weeks | Slack | Gate | Exit criterion
W00 | W0 | Foundation lock | Close G0: decisions signed, approval clocks started, pilot secured | 20 | 8 | 8 | 1.6 | -3 | G0 | All 14 ADRs signed · Meta verification submitted · pilot content owner named with dates · repo, CI and three environments live · fixture hotel seeded
S01 | W1 | Schema and tenancy | The data model everything else sits on | 3 | 5.75 | 13.75 | 2.75 | -0.75 | — | Migration clean from empty · RLS on every tenant table · isolation suite green on every endpoint built
S02 | W2 | Identity, settings, audit | Who can do what, and who did it | 5 | 5.5 | 19.25 | 3.85 | -0.5 | — | An agent at property A provably cannot read property B · settings drive the AI policy layer · every consequential action audited
S03 | W3 | Knowledge | The content system | 3 | 5 | 24.25 | 4.85 | 0 | G1 | 25 approved articles · 40 verified facts · zero unresolved contradictions · golden set v2 frozen
S04 | W4 | Retrieval and review | Find the right article, let a human approve it | 3 | 5 | 29.25 | 5.85 | 0 | — | Retrieval recall ≥90% on the golden set · nothing publishes without approval · contradictions blocked
S05 | W5 | AI core and evaluation | The answer pipeline and its guardrails | 3 | 5.5 | 34.75 | 6.95 | -0.5 | G2 | False-answer ≤2% · correct-or-correct-escalation ≥95% · every rejection logs a reason_code
S06 | W6 | Guest chat and evaluation | A stranger can hold a full conversation | 3 | 5 | 39.75 | 7.95 | 0 | — | End-to-end conversation on staging · handoff creates an inbox item · eval harness runs in CI
S07 | W7 | Chat hardening | Abuse, outages and provider failure | 6 | 4 | 43.75 | 8.75 | 1 | — | AI killed mid-conversation still yields an honest reply and a ticket · cap trip degrades gracefully
S08 | W8 | Staff inbox | The surface an agent actually uses | 4 | 5.5 | 49.25 | 9.85 | -0.5 | — | An agent triages a queue on a phone in under 60 seconds · takeover is atomic
S09 | W9 | Requests and notifications | A request nobody sees is not a request | 5 | 4.5 | 53.75 | 10.75 | 0.5 | — | Ack timestamp set by a real staff action · a request with no staff view still reaches a human
S10 | W10 | Analytics | What guests ask, and what we cannot answer | 3 | 4.5 | 58.25 | 11.65 | 0.5 | — | Dashboard numbers reconcile exactly to raw events · every tile traceable to a query
S11 | W11 | Reliability | Outbox, idempotency, redaction, observability | 5 | 5 | 63.25 | 12.65 | 0 | — | Provider outage causes delayed sends, not lost messages · no card number reaches logs
S12 | W12 | Pilot readiness | Prove it works before a guest sees it | 4 | 4.5 | 67.75 | 13.55 | 0.5 | G3 | Restore drilled and timed · three staff complete the flow unaided · runbook signed off
S13 | W13 | Launch | Train the staff, fix the content, go/no-go | 3 | 2 | 69.75 | 13.95 | 3 | — | Pilot property trained · content corrections applied · GM sign-off recorded
|  | LEAN PILOT PATH |  | 70 | 69.75 |  | 13.95 | 0.25
|  | Pilot live | Monday W14
|  | Pilot readout | W17 (G4)
|  | WhatsApp live | W18 (G5)

## 03 · Master backlog
Master backlog — every item
Filter by Sprint or Track. Acceptance criteria are testable — if you cannot test it, it is not done.
ID | Sprint | Track | Epic | Item | Description | Days | Pri | Depends on | Acceptance criteria | Status
W00-01 | W00 | Founder | Foundation | ADR review meeting, D1–D14 | 90 minutes, all fourteen discussed, an approver named for each. | 0.25 | P0 | — | All fourteen have an owner and a decision date | ☐ Not started
W00-02 | W00 | Founder | Foundation | Sign the irreversible set: D1, D5, D11, D14 | Tenancy, citation granularity, WhatsApp provider, staff i18n. | 0.25 | P0 | W00-01 | Four ADRs marked Accepted with a name and date | ✅ Done — D1/D5/D11/D14 marked Accepted, name+date in 05-kickoff-pack §2
W00-03 | W00 | Founder | Foundation | Sign remaining ten ADRs | D2, D3, D4, D6–D10, D12, D13. | 0.25 | P0 | W00-02 | Fourteen of fourteen Accepted | ✅ Done — 14/14 ADRs marked Accepted, name+date in 05-kickoff-pack §2
W00-04 | W00 | Founder | Commercial | Funding path decision | Bootstrap / Funded / Group-led. Determines team shape and therefore the schedule. | 0.5 | P0 | — | Recorded in writing; team shape fixed | ☐ Not started
W00-05 | W00 | Founder | Commercial | Second developer scoped (if funded) | Named, start date, scoped to UI and content operations, not tenancy. | 0.25 | P1 | W00-04 | Named individual with a start date | ☐ Not started
W00-06 | W00 | Founder | Commercial | One-page non-goals document | The written 'no' list for the sales conversation. PMS absent from the roadmap. | 0.25 | P0 | — | Reviewed with whoever sells | ☐ Not started
W00-07 | W00 | Founder | Compliance | Assemble and cross-check the verification pack | RFC name, RFC document, CFE/bank statement, website, display name, callable phone. | 0.5 | P0 | — | All six documents present and names match across them | ☐ Not started
W00-08 | W00 | Founder | Compliance | Submit Meta business verification | Submit Wednesday even if imperfect. A rejection is information; waiting is not. | 0.25 | P0 | W00-07 | Case ID recorded | ☐ Not started
W00-09 | W00 | Founder | Commercial | WhatsApp BSP shortlist to two | Scored on Embedded Signup, number ownership, MX coverage, webhook quality. | 0.25 | P0 | W00-08 | Two providers scored; one recommended | ☐ Not started
W00-10 | W00 | Founder | Pilot | Pilot property kickoff call | Confirm rooms, GM owner, content owner, web-first channel, baseline week. | 0.5 | P0 | — | Content owner named with 4–6 hours dated in weeks 1–3 | ☐ Not started
W00-11 | W00 | Eng | Foundation | Repo, branch protection, org setup | Protected main, PR template, CODEOWNERS. | 0.5 | P0 | — | A direct push to main is rejected | ✅ Done (e8f134b)
W00-12 | W00 | Eng | Foundation | CI skeleton: lint, typecheck, test, preview | Runs on every PR. | 0.75 | P0 | W00-11 | A PR produces a preview URL and a green check | ✅ Done (a469d5e)
W00-13 | W00 | Eng | Foundation | Three environments: local, staging, prod | No shared database between staging and prod. | 0.75 | P0 | W00-12 | Staging and prod point at different databases | ☐ Not started
W00-14 | W00 | Eng | Foundation | Error tracking + structured logging | Tenant context on every log line; PII redaction on from commit one. | 0.5 | P0 | W00-13 | A staging error carries org_id, property_id, conversation_id | ☐ Not started
W00-15 | W00 | Eng | AI | Golden set v1: format + 20 starter questions | Escalation cases written by hand; answer cases drafted from nothing yet. | 0.5 | P0 | — | File format agreed; 20 questions in the repo | 🚧 Local evidence verified — pending founder sign-off that the format is agreed
W00-16 | W00 | Founder | Pilot | Baseline question log started with the hotel | Front desk logs real guest questions for a week. This is the ground truth. | 0.25 | P0 | W00-10 | Hotel staff logging daily | ☐ Not started
W00-17 | W00 | Eng | Knowledge | Adversarial fixture hotel | Flattened menu, OCR noise, contradictory pool hours, cross-language prices, photo-only notice. | 0.5 | P0 | W00-13 | Seeded in staging; every messy case reproducible | ☐ Not started
W00-18 | W00 | Founder | Compliance | Privacy notice + DPA to Mexican counsel | LFPDPPP 2025: enumerated purposes, processor obligations explicit. | 0.25 | P0 | — | Sent; turnaround expected | ☐ Not started
W00-19 | W00 | Eng | Analytics | Event taxonomy written | 18 events including staff_message_sent, each carrying tenant and conversation context. | 0.5 | P0 | — | 18 events merged as a typed module; contract test passes; no dashboard before this exists | ✅ Done — 18 events typed module, contract test passes (90d47ac)
W00-20 | W00 | Both | Foundation | G0 review | Gate sign-off with both founders. | 0.25 | P0 | W00-03, W00-08, W00-10 | Every W00 row ticked; unsigned ADRs block S01 | ☐ Not started
S01-01 | S01 | Eng | Foundation | Schema and migrations | 25 tables: orgs, properties, users, memberships, conversations, messages, requestsv, knowledge, ai_runs, events, outbox, audit. | 3 | P0 | W00-01 | Runs clean from an empty database; ERD committed | Done (PR #5 — 25/25 db incl. clean-from-empty on scratch; 4 review rounds)
S01-02 | S01 | Eng | Foundation | Row-level security policies | RLS on every tenant table, keyed by org/property membership. Plus app-layer guard. | 2 | P0 | S01-01 | A query without tenant context returns zero rows | Done (PR #5 — zero-row AC asserted on all 21 tenant tables + withTenant guard)
S01-03 | S01 | Eng | Foundation | Cross-tenant isolation test harness | Enumerates endpoints and asserts 403/404 on foreign IDs. | 0.75 | P0 | S01-02 | Suite runs in CI and fails the build on a leak | Done (PR #5 — policy-derived enumeration + leak sweep + ci db-test job, 5 review rounds)
S02-01 | S02 | Eng | Foundation | Auth + four roles | Magic link. Platform admin, org admin, property manager, agent. | 2 | P0 | S01-01 | Each role can only reach its own surface | ✅ Done (2026-10-25: requireRole is called by src/knowledge/review.ts on every review route; tests/db/role-denial.db.test.ts proves front_desk/observer 403 with zero writes — S02-06 / issue #14)
S02-02 | S02 | Eng | Foundation | Property settings | Languages, tone, hours, escalation contacts, enabled topics, AI mode, spend caps. | 1 | P0 | S02-01 | AI policy layer reads settings, does not hardcode | Done
S02-03 | S02 | Eng | Foundation | Audit log | Who changed an answer, took over, sent, or accessed as support. | 1 | P0 | S01-01 | Every consequential action writes an audit row | Done
S02-04 | S02 | Eng | Foundation | Seed fixtures + demo property | So engineering is never blocked on hotel content. | 1 | P0 | S01-01 | `make seed` produces a fully populated property | Done
S02-05 | S02 | Eng | Knowledge | is_current retrieval filtering + re-embed job | Publish flips is_current in one transaction after embedding. | 0.5 | P0 | S02-04 | Editing an article makes its old chunks unretrievable | Done
S03-01 | S03 | Eng | Knowledge | Article editor + immutable versioning | Every edit creates a version; nothing mutates history. | 2 | P0 | S01-01 | Editing never alters a historical version | Done (2026-10-24) - article create/edit/list/version services; 95 db / 120 unit
S03-02 | S03 | Eng | Knowledge | CSV bulk import with preview | Guest directory and menus. Assisted for the first five hotels. | 1 | P0 | S03-01 | A 100-row CSV imports with a preview step and no silent failures | Done (2026-10-25) - RFC 4180 parser + pure preview, atomic commit; 107 db / 138 unit (PR #30)
S03-03 | S03 | Eng | Knowledge | property_facts table + UI | Hours, prices, distances as structured values with verified_at and source version. | 2 | P0 | S03-01 | Pool hours answered by lookup, not generation | ☐ Not started
S04-01 | S04 | Eng | Knowledge | Review-and-approve screen | Nothing publishes silently. Flags missing fields and contradictions. | 2 | P0 | S03-01 | A contradictory pair is blocked until a human resolves it | ✅ Done (2026-10-25: review queue + approve/reject + fact_resolutions, 10 denial DB tests, Next.js screen in web/; db:test 137, npm test 277)
S04-02 | S04 | Eng | AI | Chunking + embeddings | Store embeddings from day one. | 1 | P0 | S03-01 | Every published version is chunked and embedded | ✅ Done (2026-10-25: 0011_article_chunks + chunkAndPublish/backfillChunks + fetch provider adapter (DEC-3 OpenAI text-embedding-3-small); db:test 152, npm test 293)
S04-03 | S04 | Eng | AI | Hybrid retrieval | FTS + trigram + pgvector, property-scoped, returns scored chunks. | 2 | P0 | S04-02 | Recall ≥90% on the golden set's target articles | 🚧 AC-1/AC-2 done; AC-3 blocked on golden v2 (G1)
S05-01 | S05 | Eng | AI | AI service with structured output contract | JSON: decision, answer, citations, reason_code, confidence. Temperature 0. No tools. | 2 | P0 | S04-03 | Malformed output rejected server-side, never sent | ✅ Done (333 unit + 174 db; DEC-2 Gemini)
S05-02 | S05 | Eng | AI | Guardrail layer | Retrieve-gate, citation check, banned-content check, entailment pass. | 2.5 | P0 | S05-01 | No false answer survives the gate on the golden set | 🚧 AC-1/AC-2 done (citation+quote verification, banned content, sensitive/policy gate, reason codes; 356 unit + 184 db green). AC-3 (G2 ≤2% false answers) UNPROVEN — needs G1 golden set v2 + S06-03 harness.
S05-03 | S05 | Eng | AI | ai_runs + citations logging | prompt_version, model_id, retrieved chunk ids, decision, latency, cost. | 1 | P0 | S05-01 | Any historical answer reconstructable from the database | ✅ Done (180 db + 333 unit; reconstructAnswer)
S06-01 | S06 | Eng | Chat | Public property-scoped web chat | /c/{slug}, streaming, mobile-first, no login. | 2 | P0 | S05-01 | A stranger holds a full conversation on staging | 🚧 AC-1/AC-2/AC-3 met as a working surface (real HTTP round trip, signed cookie, slug-only tenant, disclosure + handoff-as-message; 374 unit + 195 db green, web:build green). AC-1's 'on staging' half UNVERIFIED here — deploy is the operator step.
S06-02 | S06 | Eng | Chat | Conversation state machine | ai_active → needs_staff → staff_active → resolved, with guest reopen. | 1.5 | P0 | S06-01 | Illegal transitions impossible at the database level | ☐ Not started
S06-03 | S06 | Eng | AI | Evaluation harness + CI job | Scores correct answer / correct escalation / false answer / needless escalation. | 1.5 | P0 | S05-02 | G2 passes on the fixture property; runs on every prompt change | ☐ Not started
S07-01 | S07 | Eng | Chat | QR + embeddable snippet | Generated QR per property; one-line embed; logo and colour only. | 0.5 | P1 | S06-01 | QR resolves to the right property on a real phone | ☐ Not started
S07-02 | S07 | Eng | Chat | AI disclosure + 'talk to a person' | Persistent, obvious, translated. | 0.5 | P0 | S06-02 | A human is reachable in one tap from any state | ☐ Not started
S07-03 | S07 | Eng | Chat | Request capture + honest acknowledgement | 'I have sent your request' — never 'on the way'. Creates a service_request. | 1 | P0 | S06-02 | No code path can claim a request is fulfilled | ☐ Not started
S07-04 | S07 | Eng | Chat | Abuse + cost protection | Turnstile, per-IP/conversation/property rate limits, daily AI spend cap. | 1 | P0 | S06-01 | Cap trip degrades to 'a team member will reply' without an error | ☐ Not started
S07-05 | S07 | Eng | Chat | Outage fallback | If AI or provider is down, say so plainly and still capture a request. | 0.5 | P0 | S07-04 | Kill the AI mid-conversation; guest still gets an honest message | ☐ Not started
S07-06 | S07 | Eng | AI | LLM transport resilience | Timeouts, retry with jitter, circuit breaker, pinned model versions, parse-failure alerting. | 0.5 | P0 | S05-01 | Both providers killed; product degrades honestly | ☐ Not started
S08-01 | S08 | Eng | Inbox | Phone-first shared inbox | Filters: needs attention, mine, unresolved, unassigned. | 2 | P0 | S06-02 | An agent triages a queue on a phone in under 60 seconds | ☐ Not started
S08-02 | S08 | Eng | Inbox | Conversation detail with AI sources | Shows the exact article version the model read. | 1 | P0 | S08-01 | Staff can see the cited text verbatim | ☐ Not started
S08-03 | S08 | Eng | Inbox | Reply, take over, assign, resolve | Takeover stops AI guest-facing replies immediately. | 1.5 | P0 | S08-01 | No race where AI replies after a takeover | ☐ Not started
S08-04 | S08 | Eng | Inbox | AI operating modes | Auto / Draft / Human-only / After-hours, feature-flagged per property. | 1 | P0 | S08-03 | Mode change applies to the next message, no deploy | ☐ Not started
S09-01 | S09 | Eng | Ops | Request lifecycle | Status, owner, timestamps, internal notes, priority, reopen. | 2 | P0 | S07-03 | request_acknowledged is set by a real staff action | ☐ Not started
S09-02 | S09 | Eng | Inbox | Knowledge-gap queue | Unanswered and flagged questions with verbatim text, language, property. | 0.5 | P0 | S05-02 | Every no_answer lands in the queue automatically | ☐ Not started
S09-03 | S09 | Eng | Inbox | One-click 'wrong or outdated' | Creates or updates a knowledge gap with context. | 0.5 | P0 | S08-02 | A flag is attributable to an ai_run | ☐ Not started
S09-04 | S09 | Eng | Inbox | Non-blocking review queue | Never gates guest delivery. Replaces Draft as the week-one mechanism. | 0.5 | P0 | S08-03 | Flagging an answer does not delay the guest reply | ☐ Not started
S09-05 | S09 | Eng | Ops | Email notifications | New request, new handoff, unassigned over 15 minutes. On by default. | 1 | P0 | S09-01 | A request with no staff view still reaches a human by email | ☐ Not started
S10-01 | S10 | Eng | Analytics | Event emission across the product | All 18 taxonomy events wired with required context. | 1.5 | P0 | W00-19 | Dashboard numbers reconcile exactly to raw events | ☐ Not started
S10-02 | S10 | Eng | Analytics | Daily rollups | Nightly SQL over events. Idempotent and re-runnable. | 1 | P0 | S10-01 | A historical date can be recomputed without drift | ☐ Not started
S10-03 | S10 | Eng | Analytics | Management dashboard | Top questions by property and language, unanswered, request volume and resolution, handoff rate. | 2 | P0 | S10-02 | Every tile traceable to a query a manager can explain | ☐ Not started
S11-01 | S11 | Eng | Hardening | Transactional outbox + worker + DLQ | Send outside the request handler; backoff; failures visible. | 1.5 | P0 | S06-01 | Provider outage delays sends, never loses them | ☐ Not started
S11-02 | S11 | Eng | Hardening | Idempotency + webhook dedupe | Unique on (channel_connection_id, channel_message_id). | 1 | P0 | S06-01 | Replaying a webhook 10× produces one message | ☐ Not started
S11-03 | S11 | Eng | Hardening | PII redaction + log hygiene | Luhn card detection, long digit runs, emails, phones. No message bodies to third parties. | 1 | P0 | S10-01 | A synthetic card number never reaches logs | ☐ Not started
S11-04 | S11 | Eng | Hardening | Observability + alerting | Webhook failures, outbox backlog, LLM errors, spend caps, p95, eval regression. | 1 | P0 | S11-01 | Every alert fires once in staging with a runbook link | ☐ Not started
S11-05 | S11 | Eng | AI | Nightly embedding reconciliation | Every current version has chunks; every chunk resolves to a current version; no orphans. | 0.5 | P0 | S02-05 | Job fails loudly on a seeded drift case | ☐ Not started
S12-01 | S12 | Eng | Hardening | Runbook + backup restore drill | LLM down, WhatsApp down, DB failover, duplicate storm, spend-cap trip, deletion request. | 1 | P0 | S11-04 | Restore completed and timed; runbook signed | ☐ Not started
S12-02 | S12 | Eng | Hardening | Accessibility + ES/EN audit | Guest chat and staff UI; a mid-range Android on hotel wifi. | 1 | P1 | S08-01 | Lighthouse a11y ≥90; no untranslated strings | ☐ Not started
S12-03 | S12 | Eng | Hardening | Load test | 300 concurrent guests on one property; 50 staff sessions. | 1 | P1 | S08-01 | p95 first token ≤3.5s at target load | ☐ Not started
S12-04 | S12 | Both | Pilot | Pilot dry run with real content | Full scripted flow with the hotel's actual staff on their real content. | 1.5 | P0 | S12-01 | Three hotel staff complete the flow unaided | ☐ Not started
S13-01 | S13 | Founder | Pilot | Staff training | Three staff, scripted flows, escalation expectations, the honest-answer rule. | 1 | P0 | S12-04 | Each staff member completes a live test conversation | ☐ Not started
S13-02 | S13 | Both | Pilot | Content corrections from the dry run | Fix what the golden set and the dry run exposed. | 0.5 | P0 | S12-04 | No known-wrong article in the published set | ☐ Not started
S13-03 | S13 | Founder | Pilot | Launch checklist + GM go/no-go | Notifications live, escalation contact confirmed, QR printed, link on the website. | 0.5 | P0 | S13-01 | Written go/no-go from the GM | ☐ Not started
WA-01 | WA | Eng | WhatsApp | Payment method on WABA | Without it, service messages beyond 1,000/month do not deliver. | 0.25 | P0 | W00-08 | Billing active; spend alert configured | ☐ Not started
WA-02 | WA | Eng | WhatsApp | Adapter: webhook ingress | Verify signature, dedupe, normalise, acknowledge under 3 seconds. | 1.5 | P0 | W00-09 | A replayed webhook produces exactly one message | ☐ Not started
WA-03 | WA | Eng | WhatsApp | Adapter: send path + 24h window | Window tracking per conversation. Templates outside, free-form inside. | 1.5 | P0 | WA-02 | Sending outside the window impossible without a template | ☐ Not started
WA-04 | WA | Eng | WhatsApp | Consent + opt-out store | Explicit consent records, STOP handling, rules isolated in the adapter. | 1 | P0 | WA-03 | Opt-out honoured across every send path | ☐ Not started
WA-05 | WA | Eng | WhatsApp | Message-efficient reply composition | One complete reply per turn. No streaming into WhatsApp — every bubble is billable. | 1 | P0 | S05-02 | A typical exchange stays within the message budget | ☐ Not started
WA-06 | WA | Eng | WhatsApp | Template submission + approval | Utility templates for outside-window replies. | 1 | P0 | W00-09 | Templates approved and sendable | ☐ Not started
WA-07 | WA | Eng | WhatsApp | Number-migration safeguards | Warn that migrating a number deletes consumer WhatsApp history. | 0.5 | P0 | W00-04 | Written acknowledgement captured in onboarding | ☐ Not started
WA-08 | WA | Eng | WhatsApp | Shadow run on one property | Run alongside web chat for a week before switching traffic. | 1 | P1 | WA-03 | Zero delivery failures across 7 days | ☐ Not started
DF-01 | DEF | Eng | Ops | Outbound webhook per property | Signed, retried events to Teams/Slack/hotel ops tools. | 1 | P1 | S09-05 | A group needs events piped into their own tools | ☐ Not started
DF-02 | DEF | Eng | Analytics | Opportunity click tracking | Booking/dining/spa link clicks, labelled opportunities, never revenue. | 0.5 | P1 | S10-01 | After the pilot, against real traffic | ☐ Not started

## 04 · Capacity
Capacity check
One person, 5 productive days per week. Above 5.0 spills forward into W13's carry-forward room.
Sprint | Week | Name | Eng days | Founder days | Total | Status | Note
W00 | W0 | Foundation lock | 4.25 | 3.75 | 8 | Over by 3.00 | 8.0 days in a 5-day week. Fits only with founder and engineer in parallel; solo it runs to mid-W1.
S01 | W1 | Schema and tenancy | 5.75 | 0 | 5.75 | Over by 0.75 | Spills into the following week.
S02 | W2 | Identity, settings, audit | 5.5 | 0 | 5.5 | Over by 0.50 | Spills into the following week.
S03 | W3 | Knowledge | 5 | 0 | 5 | Fits
S04 | W4 | Retrieval and review | 5 | 0 | 5 | Fits
S05 | W5 | AI core and evaluation | 5.5 | 0 | 5.5 | Over by 0.50 | Spills into the following week.
S06 | W6 | Guest chat and evaluation | 5 | 0 | 5 | Fits
S07 | W7 | Chat hardening | 4 | 0 | 4 | Fits
S08 | W8 | Staff inbox | 5.5 | 0 | 5.5 | Over by 0.50 | Spills into the following week.
S09 | W9 | Requests and notifications | 4.5 | 0 | 4.5 | Fits
S10 | W10 | Analytics | 4.5 | 0 | 4.5 | Fits
S11 | W11 | Reliability | 5 | 0 | 5 | Fits
S12 | W12 | Pilot readiness | 4.5 | 0 | 4.5 | Fits
S13 | W13 | Launch | 0.5 | 1.5 | 2 | Fits | Launch work plus ~3 days of carry-forward room.
|  | Total demand |  |  | 69.75
|  | Capacity (14 × 5) |  |  | 70
|  | Unallocated |  |  | 0.25

## 05 · Gates
Gates
Gate | Name | Sprint | Week | Pass criteria | If it fails
G0 | Decisions and approvals | W00 | W0 | 14 ADRs signed · verification submitted · content owner named with dates · fixture seeded | Do not start S01
G1 | Content ready | S03 | W3 | 25 approved articles · 40 verified facts · zero unresolved contradictions · golden set v2 frozen | Delay the pilot, not the build
G2 | AI quality | S05 | W5 | False-answer ≤2% · correct-or-escalation ≥95% · recall ≥90% · p95 ≤3.5s | Hard stop. Fix retrieval and content, not prompts
G3 | Pilot-ready | S12 | W12 | Isolation green · restore drilled · 3 staff unaided · outage fallback verified | Restricted launch only
— | Pilot live | S13 | W14 | Trained · content corrected · GM go/no-go recorded | Postpone a week; do not launch untrained
G4 | Pilot readout | — | W17 | Containment ≥55% · accuracy ≥95% · ack median ≤10 min · gap age ≤7 days | Do not scale sales
G5 | WhatsApp live | WA | W18 | Approved · consent tested · 7-day clean shadow run | Stay web-only
G6 | Group pilot | — | W19+ | 2–3 properties · inheritance exercised · group reporting live · questionnaire answered | No PMS-dependent group

## 06 · Critical path
Critical path
Each step blocks the next. Any slip here moves W14 one-for-one.
# | Step | Sprint | Why it blocks
1 | Hotel supplies approved content | W00–S03 | Retrieval cannot be tuned against content that has not arrived. Engineering cannot absorb this.
2 | Schema and RLS | S01 | Every later table, policy and test depends on the tenancy model.
3 | Article versioning | S03 | Citations and embeddings both hang off immutable versions.
4 | Chunking and embeddings | S04 | Retrieval, the gate and the whole guardrail chain sit downstream.
5 | Retrieval quality | S04 | Below 90% recall the gate fires constantly and containment collapses.
6 | AI contract and guardrails | S05 | Guest chat has nothing to send until the contract exists.
7 | Eval harness | S06 | Without it G2 is an opinion.
8 | Guest chat | S06 | The pilot surface.
9 | Inbox | S08 | Requests with nobody to receive them are broken promises.
10 | Notifications | S09 | The reason a request gets seen at all.
11 | Restore drill and runbook | S12 | G3 cannot pass without it, and it cannot be done after an incident.
| Not on the critical path | Analytics (S10), reliability (S11), accessibility and load (S12) — each can slip a week without moving W14.

## 07 · WhatsApp
WhatsApp track
7.75 days. Approvals start W0 (calendar time); build lands W14–16 (developer time).
ID | When | Epic | Item | Days | Acceptance
WA-01 | W0 | WhatsApp | Payment method on WABA | 0.25 | Billing active; spend alert configured
WA-02 | W14 | WhatsApp | Adapter: webhook ingress | 1.5 | A replayed webhook produces exactly one message
WA-03 | W14 | WhatsApp | Adapter: send path + 24h window | 1.5 | Sending outside the window impossible without a template
WA-04 | W15 | WhatsApp | Consent + opt-out store | 1 | Opt-out honoured across every send path
WA-05 | W15 | WhatsApp | Message-efficient reply composition | 1 | A typical exchange stays within the message budget
WA-06 | W4 | WhatsApp | Template submission + approval | 1 | Templates approved and sendable
WA-07 | W5 | WhatsApp | Number-migration safeguards | 0.5 | Written acknowledgement captured in onboarding
WA-08 | W16 | WhatsApp | Shadow run on one property | 1 | Zero delivery failures across 7 days

## 08 · Deferred
Deferred to MVP-1.5
Listed so they are not quietly re-added.
ID | Epic | Item | Description | Days | Comes back when
DF-01 | Ops | Outbound webhook per property | Signed, retried events to Teams/Slack/hotel ops tools. | 1 | A group needs events piped into their own tools
DF-02 | Analytics | Opportunity click tracking | Booking/dining/spa link clicks, labelled opportunities, never revenue. | 0.5 | After the pilot, against real traffic
— | Knowledge | Automated PDF and website extraction | The rabbit hole the first five assisted onboardings exist to avoid. | 0 | After five hotels show what actually arrives
— | Platform | Self-serve onboarding wizard | Settings form plus test chat covers 80% of the value at 20% of the cost. | 0 | From hotel four
— | Group | Brand-to-property inheritance UI | Schema supports it from S01; UI not needed until a group signs. | 0 | First group pilot
— | Inbox | Guest CSAT thumbs | The weekly accuracy audit answers the same question earlier. | 0 | MVP-1.5